## Slide 1: Examples
Object Orientated Analysis and Design
Benjamin Kenwright

## Slide 2: Outline
Revision Questions
Group Project
  Review Deliverables
Exam/Quizzes/Project Dates
Example System Problem
  Case Studey

## Slide 3: Milestone Dates
Demonstrate Date
Submission Deadline
Exam 3rd Jan 2017
  2 Hours

## Slide 4: 25th December
Last Day – Quizzes
Grade Taken

## Slide 5: Group Project
Report
Submission Date 25th December
Presentation/Demonstration
Marking Criteria/Deliverables
Submit single .zip
Student number, e.g., 20939302.zip
Report and any supporting material

## Slide 6: Case Study Example
Online Ticket Reservation System

## Slide 7: Exercise
Write down the steps you’d go through for a Online Ticket Reservation System
(5 Minutes)

## Slide 8: Example Steps
Step 1
- Before entering the system, users have to login
- Get the username and password from existing users.
- Give new users the option to sign up.
Step 2
- Get the source and destination.
- Provide a dropdown box for the date.
- Check availability of tickets.
Step 3
- If tickets are available, get the number of passengers.
- Get the name and age of all passengers.
- If tickets are not available, reschedule.
Step 4
- Print the cost of the tickets.
- Get the payment details from the user.
- Confirm the details and the ticket.
- Display confirmed ticket to the user

## Slide 9: Exercise
Given your steps, draw an Activity Diagram

## Slide 10: Activity Diagram

## Slide 11: Exercise
Extend your understanding of the system to include a Class Diagram

## Slide 12: Class Diagram

## Slide 13: Exercise
Draw a use case diagram of your solution

## Slide 14: Use Case Diagram

## Slide 15: Exercise
Draw a sequence diagram of your system

## Slide 16: Sequence Diagram

## Slide 17: Exercise
Draw a collaboration diagram of your system solution

## Slide 18: Collaboration Diagram

## Slide 19: Exercise
Draw a state chart diagram of your system

## Slide 20: State Chart Diagram

## Slide 21: Exercise
Draw a component diagram of your system

## Slide 22: Component Diagram

## Slide 23: Exercise
Draw a deployment diagram of your system

## Slide 24: Deployment Diagram

## Slide 25: Question
Write down the differences between Agile and Plan-Driven development
(5 Minutes)

## Slide 26
Project is small
Experienced teams with a wide range of abilities take part
Teams are self-starters, independent leaders and others who are self-directing
Project is an in-house project and the team co-located
System is new with lots of unknowns
Requirements must be discovered
Requirements and environment are volatile with high change rates
End-user environment is flexible
Relationship with customer is close and collaborative
Customer is readily available dedicated and co-located
High trust environment exists within the development teams and customer
Rapid value and high-responsiveness are required
Project is large
Teams include varied capabilities and skill sets
Teams are geographically distributed and/or outsourced
Project is of strategic importance
System is well understood (scope and features set)
Requirements are fairly stable
System is large and complex (critical safety/high reliability requirements)
Project stakeholders have a weak relationship with the development team
External legal concerns
Focus is on a strong, quantitative process improvement
Definition and management of process are important
Predictability and stability of process are important
Agile Plan-Driven
Answer

## Slide 27: Question
Briefly summarize the importance of using inheritance
(5 minutes)

## Slide 28: Answer
Inheritance is one of the most powerful features of object oriented programming. Most important advantages of inheritance are:
Reusability
Saves times and efforts
Closeness with the real world
Easy modification
Transitive Nature of inheritance

## Slide 29: Question
Write down what Use case diagrams are used for?

## Slide 30: Answer
To model the context of a system by enclosing all the activities of a system within a rectangle and focusing on the actors outside the system by interacting with it
To model the requirements of a system from the outside point of view

## Slide 31: Question
Write down what Interaction Diagrams and what are they used for?

## Slide 32: Answer
Interaction diagrams depict interactions of objects and their relationships. They also include the messages passed between them.
Interaction diagrams are used for modeling −
  the control flow by time ordering using sequence diagrams.
  the control flow of organization using collaboration diagrams.

## Slide 33: Question
There are two categories of elements in an object-oriented system
Major Elements & Minor Elements
Write down the the four major and three minor elements.

## Slide 34: Answer
Major
  Abstraction
  Encapsulation
  Modularity
  Hierarchy
Minor
  Typing
  Concurrency
  Persistence

## Slide 35: Question
There are two types of typing are − write them down and explain them

## Slide 36: Answer
Strong Typing − Here, the operation on an object is checked at the time of compilation, as in the programming language Eiffel
Weak Typing − Here, messages may be sent to any class. The operation is checked only at the time of execution, as in the programming language Smalltalk

## Slide 37: Question
Write down the five phases of the XP lifecycle

## Slide 38: Answer
Exploration: Determine feasibility, understand key “stories” for the first release, and develop exploratory prototypes
Planning: Agree on the date and stories for the first release
Iterations to release: Implement and test selected stories in a series of iterations. Refine the iteration plan
Productionizing: Prepare supporting materials (documentation, training, marketing), and deploy the operational system
Maintenance: Fix and enhance the deployed system

## Slide 39: Question
Write down what the advantages and disadvantages of the Spiral Model

## Slide 40: Answer

## Slide 41: Question
Write down the advantages and disadvantages of the V-Shaped Model

## Slide 42: Answer

## Slide 43: Discussion
When would you use an Iterative or Incremental approach?

## Slide 44: Summary
Review
Case Study
Example Problems/Solutions
Final Exam (January)
Group Project
Review Questions

## Slide 45: This Week
Review Slides
Coursework
Reviewing Quiz Questions
Reviewing Associated Chapter

## Slide 46: Question
Deadline for final group project submission?

## Slide 47: Answer
25th December
Also deadline for online quizzes

## Slide 48: Questions/Discussion